## Gantt Chart Data
Task | Start | End | Phase | DurationDays
M1: Project Plan Approval | 2025-10-06 | 2025-10-10 | Planning | 5
Literature Review & Research | 2025-10-06 | 2026-02-15 | Research | 133
Requirements, Ethics & Scope Definition | 2025-10-06 | 2025-10-20 | Planning | 15
Database Design (ERD + SQL Schema in SSMS) | 2025-10-20 | 2025-11-10 | Database | 22
Synthetic Data Generator (Python) | 2025-11-05 | 2025-11-20 | Database | 16
M2: Database Design Completed | 2025-11-10 | 2025-11-10 | Database | 1
Node.js/Express API Development | 2025-11-17 | 2025-12-15 | API | 29
M3: Synthetic Dataset Ready | 2025-11-20 | 2025-11-20 | Database | 1
M4: API MVP Running | 2025-12-15 | 2025-12-15 | API | 1
Dissertation Writing & Documentation | 2025-12-15 | 2026-04-25 | Documentation | 132
FastAPI ML Service (Sentiment Analysis) | 2025-12-16 | 2026-01-05 | ML/AI | 21
Integrate Sentiment into API + DB | 2026-01-05 | 2026-01-20 | ML/AI | 16
Mood Prediction Model (Regression/Ensemble) | 2026-01-15 | 2026-02-10 | ML/AI | 27
M5: Sentiment Integration Complete | 2026-01-20 | 2026-01-20 | ML/AI | 1
Frontend Dashboard (HTML/CSS/Chart.js or Power BI) | 2026-02-05 | 2026-03-10 | Frontend | 34
M6: Mood Prediction Model Complete | 2026-02-10 | 2026-02-10 | ML/AI | 1
Recommendation Engine (Rules + ML) | 2026-02-25 | 2026-03-25 | ML/AI | 29
M7: Dashboard MVP Complete | 2026-03-10 | 2026-03-10 | Frontend | 1
Evaluation, Testing & Ethics Review | 2026-03-15 | 2026-04-10 | Evaluation | 27
M8: Recommendation Engine Complete | 2026-03-25 | 2026-03-25 | ML/AI | 1
M9: Evaluation Completed | 2026-04-10 | 2026-04-10 | Evaluation | 1
Final Edits, Buffer & Submission Prep | 2026-04-20 | 2026-04-30 | Documentation | 11
M10: Dissertation Draft Complete | 2026-04-20 | 2026-04-20 | Documentation | 1
M11: Final Submission | 2026-05-01 | 2026-05-01 | Documentation | 1